## 01_Project_DashboardProjectInve
pilotage et synthèse du projet
Champ | Valeur
Project | Investment Analytics Platform
Project Owner | Faty Barbosa Monteiro
Version | 1.0
Last Update | 2026-09-03
Start Date | 2026-08-28
Status | In Progress
Current Phase | Phase 3 – Data Acquisition
Completion % | XX%

## 02_Project_Plan
Phase | Description | Status
0 | Introduction du projet | ✅ Completed
1 | Cadrage du projet | ✅ Completed
2 | Architecture des données | ✅ Completed
3 | Acquisition des données | 🔄 In Progress
4 | Data Quality | ⬜ Not Started
5 | Portfolio Construction | ⬜ Not Started
6 | Portfolio Monitoring | ⬜ Not Started
7 | Performance Analytics | ⬜ Not Started
8 | Risk Analytics | ⬜ Not Started
9 | Stress Testing | ⬜ Not Started
10 | Business Intelligence | ⬜ Not Started
11 | Executive Reporting | ⬜ Not Started

## 03_Task_Tracker
Task ID | Workstream | Task | Deliverable | Status | Priority | Dependency
T001 | Source Registry | Créer Source Registry | Source Registry | ✅ Completed | High | None
T002 | Acquisition | Développer extraction Benchmark | Script Python | 🔄 In Progress | High | T001
T003 | Acquisition | Développer extraction Securities | Script Python | ⬜ Not Started | High | T001
T004 | Acquisition | Développer extraction Market | Script Python | ⬜ Not Started | High | T001

## 04_Datasets
Dataset | Raw | Processed | Universe | Status
Benchmark Dataset | ✅ | ⬜ | ⬜ | In Progress
Securities Dataset | ✅ | ⬜ | ⬜ | In Progress
Market Dataset | ⬜ | ⬜ | ⬜ | Not Started
Fundamentals Dataset | ⬜ | ⬜ | ⬜ | Not Started
Macro Dataset | ⬜ | ⬜ | ⬜ | Not Started
FX Dataset | ⬜ | ⬜ | ⬜ | Not Started
ODD Dataset | ⬜ | ⬜ | ⬜ | Not Started
Exclusion Dataset | ⬜ | ⬜ | ⬜ | Not Started

## 05_Decision_Log
Decision ID | Status | Date | Phase | Decision | Rationale
D001 | Active | 2026-08-28 | Acquisition | OpenFIGI retenu comme source principale Securities | Couverture internationale et gratuite
D002 | Active | 2026-08-28 | Acquisition | SNB retenue pour les taux FX | Source officielle suisse

## 06_Risk_Register
Risk ID | Risk | Impact | Probability | Mitigation
R001 | Limitation des APIs gratuites | Medium |  | Prévoir source alternative
R002 | Données manquantes | High |  | Contrôles qualité renforcés